## Readme 1st
CYBERSECURITY INCIDENT RESPONSE PROGRAM MANAGEMENT PLAYBOOK
This is a generic professional work sample
Purpose | Illustrative enterprise cybersecurity incident-response program-management artifact demonstrating how an incident-response document ecosystem can be structured, governed, operationalized, and mapped to recognized frameworks.
Framework alignment | ISO/IEC 27035; ISO/IEC 27001:2022; NIST SP 800-61; NIST CSF 2.0.
What this demonstrates | Program architecture, governance, RACI/ownership, time-phased operational planning, business-function routing, control/framework traceability, maturity assessment, and prioritized gap remediation.
Confidentiality note | This version has been intentionally genericized for professional demonstration. Company names, certificate identifiers, individual names, vendor names, acquisition identifiers, and other client-specific references have been removed or generalized.
How to use | Use the operational views first: Time-Phased Ops View for crisis execution, Business Function View for executive/stakeholder routing, ISO View for assurance/audit alignment, and Gap Register & Maturity for continuous improvement.
Source context | Adapted from enterprise incident-response program work. It is an example of methodology and deliverable structure, not a representation of any current organization's certified scope, controls, maturity level, or audit status.

## IR Documents By Phase
ISO/IEC 27001 CERTIFICATION ALIGNMENT ¦ Certificate Holder: Example Enterprise LLC ¦ No. EXAMPLE-CERT-ID Certified Scope: IT Managed Services - Email Security, Logging, Security Incident, Identity Access Management, Network Operations, Cloud Infra, Admin & Physical Security Current Statement of Applicability
CYBERSECURITY IR PROGRAM MANAGEMENT PLAYBOOK - INTEGRATED INVENTORY DUAL-FRAMEWORK ALIGNMENT: ISO/IEC 27035 · ISO/IEC 27001:2022 · NIST SP 800-61r3 · NIST CSF 2.0
Document Owner: CISO / IT PMO | [9 empty] | Last Updated: May 2026
No. | Document Name | ISO/IEC 27035 Phase | ISO PDCA Stage | ISO 27001:2022 Annex A Controls | NIST SP 800-61r3 / CSF 2.0 Ref | Stakeholder / Functional Owner | Criticality | Day 0 Required | Dependencies | Validation Frequency | Status | Purpose & Strategy Notes
▶ PLAN & PREPARE (11 documents)
1 | IR Policy & Plan | Plan & Prepare | DO (Clause 8) | A.5.1; A.5.2; A.5.25; A.5.26 | GV.PO (High); GV.RR-02 (Medium) | CISO / Legal | Critical | Yes | None - foundational document | Annual + Post-Incident | Complete - refresh req'd | Authoritative Governance Baseline: Synthesizes global compliance with tactical containment lifecycles. Serves as the master bridge between global policy and active containment execution.
2 | RACI Matrix | Plan & Prepare | DO (Clause 8) | A.5.2; A.5.25; A.5.26 | GV.RR-01 (Medium) | PMO | Critical | Yes | IR Policy & Plan | Annual + Post-Incident | WIP - draft complete ready for review | Operational Accountability Mapping: Codifies execution boundaries across IT, Security, Legal, HR, and Finance. Eliminates organizational ambiguity by locking down definitive functional roles.
3 | Stakeholder & Contact Directory | Plan & Prepare | DO (Clause 8) | A.5.24; A.5.25; A.5.26 | GV.RR-02 (Medium) | PMO / Communications | Critical | Yes | RACI Matrix | As Needed | WIP - draft complete ready for review | Master contact list - internal leadership, legal, vendors, law enforcement, board, media.
7 | Pre-Authorized Vendor Roster | Plan & Prepare | DO (Clause 8) | A.5.19; A.5.20; A.5.25; A.5.26 | GV.SC-05 (Medium); GV.SC-08 (Medium) | Legal / Risk Mgmt | Important | Yes | IR Policy & Plan; Legal review | Annual | Not Started | Pre-vetted forensic, legal, and PR vendors with signed NDAs and engagement letters ready to activate. Insurance carriers require pre-authorization to cover vendor costs.
Generic professional work sample | Security Awareness Training Program Materials | Plan & Prepare | DO (Clause 8) | A.5.26; A.6.3 | PR.AT-01 (Medium); PR.AT-02 (Medium) | CISO / HR | Important | No | IR Policy & Plan; RACI Matrix | Annual + Post-Incident | Not Started | Staff-facing training - phishing, credential hygiene, social engineering awareness. Must be reviewed and updated post-incident per lessons learned.
17 | Network & System Baseline Documentation | Plan & Prepare | DO (Clause 8) | A.5.9; A.5.26; A.8.15; A.8.16 | ID.AM-01 (Medium); ID.AM-02 (Medium); DE.CM-09 (High) | CIO / IT | Important | No | None - requires infrastructure access | Annual | Not Started | Documents normal system behavior, network topology, and asset inventory for anomaly detection. Without a baseline, detecting anomalies is significantly harder. Note: A.8.15 Logging is an explicit ISO cert scope domain - log retention and review procedures must be addressed here.
35 | Communications Contact Directory | Plan & Prepare | DO (Clause 8) | A.5.24; A.5.25; A.5.26 | RS.CO-02 (High) | PMO / Communications | Critical | Yes | RACI Matrix | As Needed | COMPLETE | Master contact list with name, title, email, phone, type, and privilege flag.
39 | (Reserved / Pending Entry - Renumber or Assign) | Plan & Prepare | PLAN (Clauses 4–7) | — | — | — | — | — | — | — | N/A | Placeholder to preserve 1–42 numbering. Action required: assign a document or formally renumber inventory to 1–41 before next audit review.
40 | Document Retention & Archive Policy | Plan & Prepare | DO (Clause 8) | A.5.1; A.5.25; A.5.26; A.5.33; A.8.10 | RS.AN-07 (High) | Legal / PMO | Important | No | Legal Hold Notice; IR Policy & Plan | Annual | Not Started | Defines retention periods, access controls, and archiving for all incident documentation. Typically 3–7 years depending on jurisdiction and regulation.
41 | Third-Party Risk Assessment Template | Plan & Prepare | DO (Clause 8) | A.5.19; A.5.20; A.5.21; A.5.26 | GV.SC-07 (Low); GV.SC-08 (Medium) | Legal / CISO | Important | No | IR Policy & Plan; Legal Hold Notice | Annual | Not Started | Structured assessment of vendor and partner security posture - pre- and post-incident. Many breaches originate through third-party access.
42 | Abbreviations & Terminology Reference | Plan & Prepare | DO (Clause 8) | A.5.1; A.5.25; A.5.26 | NIST SP 800-61 Rev. 3 - Appendix A & B | PMO | Supporting | No |  | Annual | COMPLETE | Plain-language glossary of all IR abbreviations and terms for non-technical stakeholders.
▶ DETECTION & REPORTING (4 documents)
5 | Incident Severity & Categorization Matrix | Detection & Reporting | DO (Clause 8) | A.5.25; A.5.26; A.5.29; A.5.30; A.8.13 | RS.AN-01 (High) | CISO | Critical | Yes | IR Policy & Plan | Annual | Not Started | The Operational Trigger Mechanism: Translates complex technical event parameters into high-visibility business impact tiers. Dictates precisely when an incident scales to an executive-level crisis requiring CXO intervention.
11 | Incident Chronology Log* | Detection & Reporting | CHECK (Clause 9) | A.5.26; A.5.27 | RS.AN-06 (High) | CIO / IT | Critical | Yes | None - initiated at incident declaration | Per Incident | Not Started | Time-stamped record of every action taken from initial detection through closure. Must be initiated within the first hour of incident activation.
18 | Indicators of Compromise (IOC) Tracker | Detection & Reporting | DO (Clause 8) | A.5.7; A.5.26; A.8.16 | DE.AE-07 (High); DE.AE-03 (High) | CISO | Critical | Yes | Incident Chronology Log | Per Incident | Not Started | Logs all confirmed IOCs - IPs, domains, file hashes, registry keys - shared with security tools. Share with forensic vendor and law enforcement immediately.
25 | Acquired Entity Escalation Protocol | Detection & Reporting | DO (Clause 8) | A.5.25; A.5.26 | GV.SC-07 (Medium) | CIO / IT (Acquired Entity) | Important | No | RACI Matrix; IR Policy & Plan | As Needed / Post-Incident | Not Started | M&A Infrastructure Boundary Plan: Explicitly isolates legacy architecture from newly acquired networks, establishing separate, clean visibility protocols across distinct IT environments. Added to address Acquired Entity integration exposure identified post-acquisition.
▶ ASSESSMENT & DECISION (3 documents)
13 | IR Ransom Refusal Generic Gantt | Assessment & Decision | DO (Clause 8) | A.5.26; A.5.29 | RS.MA-03 (High); RS.MA-04 (High) | TBD | Supporting | No | WBS Project Plan | Post-Incident | WIP | Visual timeline of all response phases from Day 0 through Day 60. IR Ransom Refusal Generic Gantt.xlsx; Post Ransom Refusal Generic.xlsx (Legal, CIO, IA own).
23 | Hacker Threat & Regulatory Response Matrix* | Assessment & Decision | CHECK (Clause 9) | A.5.24; A.5.26; A.5.31 | GV.OC-03 (Medium); RS.CO-02 (High) | Legal / CISO | Critical | Yes | Regulatory Notification Tracker; Legal Hold Notice | Post-Incident | WIP - draft complete ready for review | Maps every known threat action to regulations, legal consequences, and required responses. Hacker Threat Response Matrix Template.xlsx
26 | Post-Ransom Refusal Response Plan | Assessment & Decision | DO (Clause 8) | A.5.1; A.5.25; A.5.26; A.5.29 | RS.MA-03 (High); RS.MI-01 (High); RS.MI-02 (High) | PMO / CISO | Important | No | Post-Ransom Refusal Plan; IR Policy | Post-Incident | WIP - draft complete ready for review | Action plan for organizations that decline to pay ransom - Day 0 through Day 60 with Gantt. Post Ransom NIST Milestone Plan v2.xlsx
▶ RESPONSE & RECOVERY (17 documents)
4 | War Room Call Schedule & Bridge Info | Response & Recovery | DO (Clause 8) | A.5.26 | RS.CO-02 (High) | PMO | Critical | Yes | RACI Matrix | As Needed | WIP | Central coordination hub for all active incident calls/meetings. Source of truth for cadences, attendees, and dial-in details so stakeholders know exactly where to be and when.
6 | Jump Bag / Forensic Hardware Checklist | Response & Recovery | DO (Clause 8) | A.5.26; A.5.28; A.5.29; A.5.30; A.8.13 | GV.RR-03 (Low) | IT / Forensics | Important | Yes | IR Policy & Plan | Annual | Not Started | Equipment and tools that must be procured and ready before an incident - laptops, drives, write blockers. Prevents Day 0 delays when hardware is urgently needed.
10 | Business Continuity & Disaster Recovery Plan | Response & Recovery | PLAN/DO (Clauses 5–8) | A.5.26; A.5.29; A.5.30; A.8.13 | PR.IR-03 (High) | BC / DR & CISO | Important | No | IR Policy & Plan | Annual | Not Started | Enterprise Resilience Alignment: Hand-off criteria from technical IT incident containment to Business-owned continuity teams. (Document managed by BC team; IT maintains trigger ownership.) Critical for RTO validation. Potential ISO observation: A.5.29 and A.5.30 (BC/DR integration) currently have no coverage - requires owner decision from CISO and CIO.
12 | IR WBS Project Plan | Response & Recovery | DO (Clause 8) | A.5.26 | RS.MA-01 (High); RS.MA-04 (High) | PMO | Critical | Yes | IR Policy & Plan; RACI Matrix | Post-Incident | WIP - draft complete ready for review | Master project plan tracking required activities of each workstream with owners, timelines, and status. IR WBE Project Plan.xlsx
14 | IR Metrics Template | Response & Recovery | ACT (Clause 10) | A.5.26; A.5.27; A.5.30; A.8.8 | DE.AE-04 (High); ID.IM-01 (Medium) | PMO / CISO | Important | No | IR Checklist; Severity Category | Post-Incident | WIP - draft complete ready for review | Tracks MTTD, MTTC, MTTR, Dwell Time, Patch Latency, Backup Integrity, and ALE. IR Master Metrics Template.xlsx
15 | Daily Executive Status Update Template | Response & Recovery | CHECK (Clause 9) | A.5.26 | RS.CO-03 (High); RC.CO-03 (High) | PMO | Critical | Yes | RACI Matrix; Stakeholder Directory | Post-Incident | WIP | Traffic light dashboard/summary for SLT: what was done, what is blocked, what is next, decisions needed. Cyber Exec Update Simple.docx
16 | Meeting Log* | Response & Recovery | DO (Clause 8) | A.5.26 | RS.AN-06 (High) | PMO | Important | No | RACI Matrix; Stakeholder Directory | Per Incident | WIP | Running record of every meeting - attendees, goals, decisions, and action items. IR Comms and Meeting Templates.xlsx
19 | IR Checklist (24/48/72hr + Beyond) | Response & Recovery | DO (Clause 8) | A.5.26 | RS.MA-01 (High); RS.MI-01 (High); RS.MI-02 (High) | PMO / CISO | Critical | Yes | IR Checklist; Severity Category; RACI Matrix | Post-Incident | WIP - draft complete ready for review | Time-phased checklist of critical required actions from Hour 1 through Day 30. Incident Response 24-48-72 Checklist.xlsx
20 | BEC / Whaling Tactical Playbook | Response & Recovery | DO (Clause 8) | A.5.26; A.8.12 | RS.MI-01 (High); RS.RP-01 (High) | CISO / Legal | Critical | Yes | IR Policy & Plan; RACI Matrix | Annual + Post-Incident | Not Started | Day 0 Cash & Credential Protection: Rapid-response workflows for BEC and executive whaling attacks. Maps wire recalls, payment freezes, and executive notifications to clear timelines. Built for the 6/18 tabletop. Note: Relocated from standalone 'Responses' phase to align with ISO/IEC 27035 Phase 3 (Response). Identity access management is an explicit ISO cert scope domain - IAM-specific credential compromise steps must be embedded here.
21 | Evidence Collection & Chain of Custody Log | Response & Recovery | DO (Clause 8) | A.5.26; A.5.28 | RS.AN-07 (High) | Legal / Forensics | Critical | Yes | IR Policy & Plan; Legal Hold Notice Template | Per Incident | Not Started | Documents every piece of evidence gathered - system, location, handler, and custody transfer. Legally required for law enforcement engagement and litigation.
22 | Forensic Hardware & Evidence Handling Checklist | Response & Recovery | DO (Clause 8) | A.5.26; A.5.28 | RS.AN-07 (High) | IT / Forensics | Critical | Yes | Chain of Custody Log; IR Policy & Plan | Per Incident | Not Started | Ensures proper acquisition, labeling, and preservation of all forensic artifacts. Must be in place before forensic imaging begins.
24 | Backup Integrity Validation Log | Response & Recovery | DO (Clause 8) | A.5.26; A.5.30; A.8.13 | PR.DS-11 (High); RC.RP-03 (High) | CIO / IT | Important | No | Network & System Baseline Documentation | Semi-Annual | Not Started | Documents backup restoration test results - confirms backups are clean and viable. Must be validated before any system recovery begins.
27 | System Recovery & Rebuild Runbook | Response & Recovery | DO (Clause 8) | A.5.9; A.5.26; A.5.30; A.8.13; A.8.15; A.8.16 | RC.RP-02 (High); RC.RP-05 (High) | CIO / IT | Important | No | Baseline Documentation; Forensic findings | Per Incident | Not Started | Step-by-step technical instructions for rebuilding each critical system from a clean baseline. Should exist per system type - validated pre-incident.
34 | Communications Log | Response & Recovery | DO (Clause 8) | A.5.24; A.5.26 | RS.CO-02 (High); RS.AN-06 (High) | PMO / Legal | Critical | Yes | Stakeholder Directory; War Room Call Schedule | Per Incident | Not Started | Running record of every internal and external communication made throughout the engagement.
36 | Regulatory Notification Tracker | Response & Recovery | CHECK (Clause 9) | A.5.2; A.5.24; A.5.25; A.5.26; A.5.31 | GV.OC-03 (Medium); RS.CO-02 (High) | Legal / Compliance | Critical | Yes | Legal Hold Notice; IR Policy & Plan | Per Incident | COMPLETE | Tracks every notification obligation - deadline, status, confirmation, and responsible party.
37 | External Communications & Media Plan | Response & Recovery | DO (Clause 8) | A.5.1; A.5.24; A.5.25; A.5.26 | RS.CO-03 (High); RC.CO-04 (High) | Communications / Legal | Important | No | Regulatory Notification Tracker; Legal Hold Notice | Post-Incident | Not Started | Pre-approved messaging templates for customers, employees, media, and regulators. Must be drafted and approved before an incident - not during.
38 | Insurance Submission Package Template | Response & Recovery | DO (Clause 8) | A.5.26; A.5.31 | GV.RM-03 (Medium) | Legal / Risk Mgmt | Important | No | Regulatory Notification Tracker; Forensic findings | Per Incident | Not Started | Structured package for cyber insurance claim - forensic summary, timelines, controls posture. Carriers have specific documentation requirements - know them in advance.
▶ LESSONS LEARNED & IMPROVEMENT (7 documents)
9 | Tabletop Exercise Scenarios | Lessons Learned & Improvement | ACT (Clause 10) | A.5.25; A.5.26; A.5.27; A.6.3 | ID.IM-02 (High) | CISO / PMO | Important | No | IR Policy & Plan; Severity Category | Annual + Post-Incident | Not Started | Pre-incident simulation scripts to test team readiness - scenario-based walkthroughs. Update after every incident to reflect new attack patterns.
28 | Lessons Learned Report | Lessons Learned & Improvement | ACT (Clause 10) | A.5.26; A.5.27 | ID.IM-03 (High); RC.RP-06 (High) | CISO / PMO | Critical | No | IR Checklist; All Phase 3 documents complete | Post-Incident | Not Started | Formal post-incident review - what worked, what failed, root causes, and what must change. Must be completed within 30 days of incident closure.
29 | Final Incident Report - Executive | Lessons Learned & Improvement | ACT (Clause 10) | A.5.1; A.5.25; A.5.26; A.5.27 | RC.RP-06 (High); RS.CO-03 (High) | PMO / Legal | Critical | No | Lessons Learned Report; All Phase 3 documents | Post-Incident | WIP - draft complete ready for review | Board-ready comprehensive record - facts, scope, impact, response, and remediation plan. Data Breach Executive Report Template.docx
30 | Remediation Roadmap | Lessons Learned & Improvement | ACT (Clause 10) | A.5.1; A.5.25; A.5.26; A.5.27; A.8.8 | ID.IM-03 (High); ID.RA-06 (High) | CIO / CISO | Important | No | Lessons Learned Report; Control Gap Analysis | Post-Incident | Not Started | Prioritized plan to close all control gaps - owners, timelines, costs, and success criteria. Board-visible - requires CIO and CISO approval.
31 | Post-Incident Change Management Log | Lessons Learned & Improvement | ACT (Clause 10) | A.5.27; A.5.28 | ID.IM-04 (High) | CISO | Important | No | IR Policy & Plan; Lessons Learned Report | Annual + Post-Incident | Not Started | Continuous Improvement Matrix: Captures post-incident architecture enhancements and all changes made to the IR plan. Translates security findings into permanent, hardened adjustments to baseline ISO protocols. Note: Control mapping corrected - A.5.28 removed (evidence collection); aligned to A.5.27 (learning from incidents) and A.5.1 (policy governance).
32 | Training Material Review & Update Log | Lessons Learned & Improvement | ACT (Clause 10) | A.5.26; A.5.27; A.6.3 | ID.IM-03 (High); PR.AT-02 (Medium) | CISO / HR | Important | No | Lessons Learned Report; Training Materials | Annual + Post-Incident | Not Started | Records all updates to security awareness and IR training content and rationale. Documents that training was updated as a result of this incident.
33 | Tabletop Exercise Update - Post Incident | Lessons Learned & Improvement | ACT (Clause 10) | A.5.25; A.5.26; A.5.27; A.6.3 | ID.IM-02 (High) | CISO / PMO | Important | No | Lessons Learned Report; IR Policy & Plan | Annual + Post-Incident | Not Started | Revised tabletop scenarios incorporating attack methodology from this incident. Schedule within 90 days of closure. NOTE: Tabletop Exercise scheduled for 6/18; f/u with Lead Outside Counsel to build feedback loop into internal workflows.

## Time-Phased Ops View
Time-Phased Operational View of Document Inventory
This table groups required incident-response documents by the hour for use during an active crisis. It provides an enterprise-wide "what to do" guide. Document status can be maintained in the integrated inventory tab.
Category | Hour-by-Hour Prioritized Activities | Sample Mapped Artifacts (From the 52-Doc Inventory) | Primary Reviewing / Approving Stakeholders
The Triage & Immediate Isolation Pack | Hours 0 - 6: • Stop the bleeding • Confirm the incident • Isolate environment, network segments, etc. • Stand-up the war room • Do not wipe forensic evidence (confirm staff "know" what this means) | IR Policy & Plan | CISO
|  | RACI Matrix | IT Operations / Managed Service Provider
|  | Severity & Categorization Matrix | SOC / Incident Manager
|  | Incident Chronology Log | SOC / Incident Manager
|  | War Room Call Schedule & Bridge Info | SOC / Incident Manager
The Regulatory Clock & Legal Shield Pack | Hours 6 - 24: • Engage counsel • Document threat intelligence • Assess regulatory and compliance ETAs (GDPR 72hr, SEC, etc.) • Lock down financial wire permissions, if applicable. | Legal Counsel & Attorney-Client Privilege SOP | Legal Counsel (Legal Counsel)
|  | Global Regulatory Notification Matrix | Outside Counsel (Lead Outside Counsel)
|  | Regulatory Notification Tracker | Internal Audit or Legal Counsel (Legal Counsel)
|  | Cyber Insurer Notification Flow | CFO Organization
|  | CFO Wire Freeze & Financial Controls Protocol | CFO Organization
The Eradication & Prioritized Recovery Pack | Hours 24 - 72 (Days 1-3): • Deep forensic analysis • Perimeter hardening • Backup verification, etc. • Execute respective localized playbooks | Business Email Compromise (BEC) Playbook | CIO (CIO)
|  | Ransomware Refusal & Decision Framework | IT Infrastructure Teams
|  | Forensic Evidence Acquisition & Chain of Custody Log | External Forensics and formally approved Vendors
|  | Backup Integrity Validation Procedure | External Forensics and formally approved Vendors
|  | System Recovery Sequencing Runbook | External Forensics and formally approved Vendors
The Executive Governance & Closeout Pack | Days 4 - 30 (Weeks 1-4): • Clean up the environment • Compile board-ready reports • Identify systemic control gaps • Establish long-term remediation roadmap (Jackie to break down by week) | Root Cause Analysis (RCA) Template | Example Enterprise CIO & CISO
|  | Board-Ready Executive Incident Report Template | Example Enterprise CIO & CISO
|  | Remediation Roadmap & Control Hardening Framework | Example Enterprise CISO, SOC / Incident Manager
|  | Post-Incident Change Management Log | SOC / Incident Manager
|  | Post-Incident Lessons Learned Process | Example Enterprise CIO, CISO, SOC / Incident Manager

## Business Function View
Governance: Business Functions View
This table aligns incident-response documentation to business functions and leadership so stakeholders can focus on their responsibilities from a non-technical point of view.
Category | Core Operational Focus | Sample Mapped Artifacts (From the 52-Doc Inventory) | Primary Reviewing / Approving Stakeholders
The Executive Steering & Corporate Risk Pack | Overarching corporate policy, commercial risk mitigation, M&A boundary controls, insurance coverage triggers, and public relations protection. | Overarching IR Policy | CIO (CIO)
|  | Ransom Refusal Decision Framework | CIO (CIO)
|  | Corporate Communications & Press Templates | Legal Counsel (Legal Counsel)
|  | M&A Entity Integration / Acquired-Entity Boundary Control Policy | Corporate Communications
Parent Company Notification Trigger Matrix
The Core Security Operations & Intel Kit | The Day-to-Day tactical baseline for identifying, prioritizing, analyzing, and documenting threat actor movements inside the environment. | SIEM Triage & Alarm Procedures | CISO
|  | Threat Intelligence Ingestion Flow | SOC Manager / Cyber Ops
|  | IOC Tracker & Threat Hunting Queries | Internal Audit
Incident Severity & Categorization Matrix
Forensic Jump Bag Checklist
The IT Infrastructure & Provider Rebuild Runbooks | Infrastructure containment, configuration validation, directory service recovery, and identity/access adjustments handled by distributed operational tracks. | Network Segmentation & Boundary Isolation Playbook | IT Operations (Netops)
|  | Credential Revocation & Active Directory Lock Step | Managed Service Provider Track Leads
|  | System Recovery & Baseline Rebuild Runbook | IAM/Directory Service Admins
Backup Integrity Validation Procedure
The HR, Legal, & Compliance Shield | Employee investigations, insider threats, whistleblower workflows, independent regulatory reporting, and internal disciplinary tracking. | Insider Threat & Employee Investigation Protocol | Legal Counsel (Legal Counsel)
|  | HR Disciplinary Action Reference Guide | Human Resources
|  | Global Regulatory & Privacy Notification Matrix | Outside Counsel
|  | Chain of Custody & Evidence Log | Compliance Officers

## ISO View
ISO Alignment (The Auditor's View)
The strategy: align the incident-response document set to the organization’s ISO/IEC 27001 scope and Statement of Applicability, while maintaining cross-framework traceability to ISO/IEC 27035, NIST SP 800-61 and NIST CSF 2.0. The goal is to demonstrate a functioning, evidence-based incident-response capability rather than a generic template.
Category | Core Operational Focus | Sample Mapped Artifacts (From the 52-Doc Inventory) | Primary Reviewing / Approving Stakeholders
Bundle 3.1: Certified Incident Management & Governance Domain | Explicitly satisfies ISO 27001 Annex A.5.25 & A.5.26 by defining responsibilities, communication paths, and post-incident continuous improvement. | * IR Policy & Plan | * CISO
|  | * Enterprise IR RACI Matrix | * Internal Audit
|  | * Post-Incident Review (Lessons Learned) Process | * Third-Party ISO Auditors
* Root Cause Analysis (RCA) Workflow
* Statement of Applicability (SoA) Control Mapping Index
Bundle 3.2: Identity Access Management (IAM) Response Domain | Directly covers the certified IAM scope domain; handles session timeouts, credential compromises, privilege escalation, and domain controller contamination. | * Credential Revocation & Session Timeout Protocol | * CISO
|  | * Privilege Escalation Detection Runbook | * IAM Engineering Track
|  | * Active Directory / Identity Infrastructure Containment Steps | * IT Operations
* MFA Bypass & Account Takeover Response Procedure
Bundle 3.3: Logging & Forensic Evidence Protection Domain | Directly covers the certified Security Logging scope domain (Annex A.8.15 & A.8.16); ensures SIEM telemetry and forensic artifacts are legally defensible. | * Sentinel SIEM Log Retention & Protection SOP | * SOC Manager / Lead Forensics
|  | * Forensic Evidence Acquisition & Chain of Custody Log | * IT Infrastructure Admins
|  | * Incident Chronology Log Template | * Legal Counsel
* Network & System Performance Baseline Documentation
Bundle 3.4: Cloud Infra & Network Operations (NetOps) Domain | Covers email security, cloud boundaries (Wiz/Azure/AWS), and network isolation to protect core operational availability during an ongoing event. | * Network Segmentation & CATO/Palo Alto Boundary Rules | * IT Operations (Netops)
|  | * Cloud Infrastructure (Wiz/Defender) Incident Playbook | * Managed Service Provider Track Leads
|  | * Email Security & Phishing/Phishing-Infrastructure Triage Flow | * Cloud Architecture Team
* Supplier/M&A (Acquired Entity) Architecture Separation Procedure
How to use this to control tomorrow's meeting:
Use the three summary views first when presenting this playbook to executive sponsor. They provide actionable views for incident managers, business/legal stakeholders, and audit/assurance stakeholders without requiring the reviewer to start with the full inventory.
This playbook is designed to provide actionable viewpoints not a verbose document list: one view for technical incident management, one for routing responsibilities across business functions, and one optimized for regulatory and ISO assurance readiness.

## IR Documents By Number
ISO/IEC 27001 CERTIFICATION ALIGNMENT ¦ Certificate Holder: Example Enterprise LLC ¦ Test Mark No. EXAMPLE-CERT-ID ¦ Certified Scope: IT Managed Services — Email Security, Logging, Security Incident, Identity Access Management, Network Operations, Cloud Infra, Admin & Physical Security ¦ Current Statement of Applicability
CYBERSECURITY IR PROGRAM MANAGEMENT PLAYBOOK — INTEGRATED INVENTORY ¦ DUAL-FRAMEWORK ALIGNMENT: ISO/IEC 27035 · ISO/IEC 27001:2022 · NIST SP 800-61r3 · NIST CSF 2.0
Document Owner: CISO / IT PMO |  |  |  |  | Version: 3.0 (Restored Operational Fields + Gap Register) |  |  |  |  | Last Updated: May 2026
No. | Document Name | ISO/IEC 27035 Phase | ISO PDCA Stage | ISO 27001:2022 Annex A Controls | NIST SP 800-61r3 / CSF 2.0 Ref | Stakeholder / Functional Owner | Criticality | Day 0 Required | Dependencies | Validation Frequency | Status | Purpose & Strategy Notes
1 | IR Policy & Plan | Plan & Prepare | DO (Clause 8) | A.5.1; A.5.2; A.5.25; A.5.26 | GV.PO (High); GV.RR-02 (Medium) | CISO / Legal | Critical | Yes | None — foundational document | Annual + Post-Incident | Complete - refresh req'd | Authoritative Governance Baseline: Synthesizes global compliance with tactical containment lifecycles. Serves as the master bridge between global policy and active containment execution.
2 | RACI Matrix | Plan & Prepare | DO (Clause 8) | A.5.2; A.5.25; A.5.26 | GV.RR-01 (Medium) | PMO | Critical | Yes | IR Policy & Plan | Annual + Post-Incident | WIP - draft complete ready for review | Operational Accountability Mapping: Codifies execution boundaries across IT, Security, Legal, HR, and Finance. Eliminates organizational ambiguity by locking down definitive functional roles.
3 | Stakeholder & Contact Directory | Plan & Prepare | DO (Clause 8) | A.5.24; A.5.25; A.5.26 | GV.RR-02 (Medium) | PMO / Communications | Critical | Yes | RACI Matrix | As Needed | WIP - draft complete ready for review | Master contact list — internal leadership, legal, vendors, law enforcement, board, media.
4 | War Room Call Schedule & Bridge Info | Response & Recovery | DO (Clause 8) | A.5.26 | RS.CO-02 (High) | PMO | Critical | Yes | RACI Matrix | As Needed | WIP | Central coordination hub for all active incident calls/meetings. Source of truth for cadences, attendees, and dial-in details so stakeholders know exactly where to be and when.
5 | Incident Severity & Categorization Matrix | Detection & Reporting | DO (Clause 8) | A.5.25; A.5.26; A.5.29; A.5.30; A.8.13 | RS.AN-01 (High) | CISO | Critical | Yes | IR Policy & Plan | Annual | Not Started | The Operational Trigger Mechanism: Translates complex technical event parameters into high-visibility business impact tiers. Dictates precisely when an incident scales to an executive-level crisis requiring CXO intervention.
6 | Jump Bag / Forensic Hardware Checklist | Response & Recovery | DO (Clause 8) | A.5.26; A.5.28; A.5.29; A.5.30; A.8.13 | GV.RR-03 (Low) | IT / Forensics | Important | Yes | IR Policy & Plan | Annual | Not Started | Equipment and tools that must be procured and ready before an incident — laptops, drives, write blockers. Prevents Day 0 delays when hardware is urgently needed.
7 | Pre-Authorized Vendor Roster | Plan & Prepare | DO (Clause 8) | A.5.19; A.5.20; A.5.25; A.5.26 | GV.SC-05 (Medium); GV.SC-08 (Medium) | Legal / Risk Mgmt | Important | Yes | IR Policy & Plan; Legal review | Annual | Not Started | Pre-vetted forensic, legal, and PR vendors with signed NDAs and engagement letters ready to activate. Insurance carriers require pre-authorization to cover vendor costs.
8 | Security Awareness Training Program Materials | Plan & Prepare | DO (Clause 8) | A.5.26; A.6.3 | PR.AT-01 (Medium); PR.AT-02 (Medium) | CISO / HR | Important | No | IR Policy & Plan; RACI Matrix | Annual + Post-Incident | Not Started | Staff-facing training — phishing, credential hygiene, social engineering awareness. Must be reviewed and updated post-incident per lessons learned.
9 | Tabletop Exercise Scenarios | Lessons Learned & Improvement | ACT (Clause 10) | A.5.25; A.5.26; A.5.27; A.6.3 | ID.IM-02 (High) | CISO / PMO | Important | No | IR Policy & Plan; Severity Category | Annual + Post-Incident | Not Started | Pre-incident simulation scripts to test team readiness — scenario-based walkthroughs. Update after every incident to reflect new attack patterns.
10 | Business Continuity & Disaster Recovery Plan | Response & Recovery | PLAN/DO (Clauses 5–8) | A.5.26; A.5.29; A.5.30; A.8.13 | PR.IR-03 (High) | BC / DR & CISO | Important | No | IR Policy & Plan | Annual | Not Started | Enterprise Resilience Alignment: Hand-off criteria from technical IT incident containment to Business-owned continuity teams. (Document managed by BC team; IT maintains trigger ownership.) Critical for RTO validation. Potential ISO observation: A.5.29 and A.5.30 (BC/DR integration) currently have no coverage — requires owner decision from CISO and CIO.
11 | Incident Chronology Log* | Detection & Reporting | CHECK (Clause 9) | A.5.26; A.5.27 | RS.AN-06 (High) | CIO / IT | Critical | Yes | None — initiated at incident declaration | Per Incident | Not Started | Time-stamped record of every action taken from initial detection through closure. Must be initiated within the first hour of incident activation.
12 | IR WBS Project Plan | Response & Recovery | DO (Clause 8) | A.5.26 | RS.MA-01 (High); RS.MA-04 (High) | PMO | Critical | Yes | IR Policy & Plan; RACI Matrix | Post-Incident | WIP - draft complete ready for review | Master project plan tracking required activities of each workstream with owners, timelines, and status. IR WBE Project Plan.xlsx
13 | IR Ransom Refusal Generic Gantt | Assessment & Decision | DO (Clause 8) | A.5.26; A.5.29 | RS.MA-03 (High); RS.MA-04 (High) | TBD | Supporting | No | WBS Project Plan | Post-Incident | WIP | Visual timeline of all response phases from Day 0 through Day 60. IR Ransom Refusal Generic Gantt.xlsx; Post Ransom Refusal Generic.xlsx (Legal, CIO, IA own).
14 | IR Metrics Template | Response & Recovery | ACT (Clause 10) | A.5.26; A.5.27; A.5.30; A.8.8 | DE.AE-04 (High); ID.IM-01 (Medium) | PMO / CISO | Important | No | IR Checklist; Severity Category | Post-Incident | WIP - draft complete ready for review | Tracks MTTD, MTTC, MTTR, Dwell Time, Patch Latency, Backup Integrity, and ALE. IR Master Metrics Template.xlsx
15 | Daily Executive Status Update Template | Response & Recovery | CHECK (Clause 9) | A.5.26 | RS.CO-03 (High); RC.CO-03 (High) | PMO | Critical | Yes | RACI Matrix; Stakeholder Directory | Post-Incident | WIP | Traffic light dashboard/summary for SLT: what was done, what is blocked, what is next, decisions needed. Cyber Exec Update Simple.docx
16 | Meeting Log* | Response & Recovery | DO (Clause 8) | A.5.26 | RS.AN-06 (High) | PMO | Important | No | RACI Matrix; Stakeholder Directory | Per Incident | WIP | Running record of every meeting — attendees, goals, decisions, and action items. IR Comms and Meeting Templates.xlsx
17 | Network & System Baseline Documentation | Plan & Prepare | DO (Clause 8) | A.5.9; A.5.26; A.8.15; A.8.16 | ID.AM-01 (Medium); ID.AM-02 (Medium); DE.CM-09 (High) | CIO / IT | Important | No | None — requires infrastructure access | Annual | Not Started | Documents normal system behavior, network topology, and asset inventory for anomaly detection. Without a baseline, detecting anomalies is significantly harder. Note: A.8.15 Logging is an explicit ISO cert scope domain — log retention and review procedures must be addressed here.
18 | Indicators of Compromise (IOC) Tracker | Detection & Reporting | DO (Clause 8) | A.5.7; A.5.26; A.8.16 | DE.AE-07 (High); DE.AE-03 (High) | CISO | Critical | Yes | Incident Chronology Log | Per Incident | Not Started | Logs all confirmed IOCs — IPs, domains, file hashes, registry keys — shared with security tools. Share with forensic vendor and law enforcement immediately.
19 | IR Checklist (24/48/72hr + Beyond) | Response & Recovery | DO (Clause 8) | A.5.26 | RS.MA-01 (High); RS.MI-01 (High); RS.MI-02 (High) | PMO / CISO | Critical | Yes | IR Checklist; Severity Category; RACI Matrix | Post-Incident | WIP - draft complete ready for review | Time-phased checklist of critical required actions from Hour 1 through Day 30. Incident Response 24-48-72 Checklist.xlsx
20 | BEC / Whaling Tactical Playbook | Response & Recovery | DO (Clause 8) | A.5.26; A.8.12 | RS.MI-01 (High); RS.RP-01 (High) | CISO / Legal | Critical | Yes | IR Policy & Plan; RACI Matrix | Annual + Post-Incident | Not Started | Day 0 Cash & Credential Protection: Rapid-response workflows for BEC and executive whaling attacks. Maps wire recalls, payment freezes, and executive notifications to clear timelines. Built for the 6/18 tabletop. Note: Relocated from standalone 'Responses' phase to align with ISO/IEC 27035 Phase 3 (Response). Identity access management is an explicit ISO cert scope domain — IAM-specific credential compromise steps must be embedded here.
21 | Evidence Collection & Chain of Custody Log | Response & Recovery | DO (Clause 8) | A.5.26; A.5.28 | RS.AN-07 (High) | Legal / Forensics | Critical | Yes | IR Policy & Plan; Legal Hold Notice Template | Per Incident | Not Started | Documents every piece of evidence gathered — system, location, handler, and custody transfer. Legally required for law enforcement engagement and litigation.
22 | Forensic Hardware & Evidence Handling Checklist | Response & Recovery | DO (Clause 8) | A.5.26; A.5.28 | RS.AN-07 (High) | IT / Forensics | Critical | Yes | Chain of Custody Log; IR Policy & Plan | Per Incident | Not Started | Ensures proper acquisition, labeling, and preservation of all forensic artifacts. Must be in place before forensic imaging begins.
23 | Hacker Threat & Regulatory Response Matrix* | Assessment & Decision | CHECK (Clause 9) | A.5.24; A.5.26; A.5.31 | GV.OC-03 (Medium); RS.CO-02 (High) | Legal / CISO | Critical | Yes | Regulatory Notification Tracker; Legal Hold Notice | Post-Incident | WIP - draft complete ready for review | Maps every known threat action to regulations, legal consequences, and required responses. Hacker Threat Response Matrix Template.xlsx
24 | Backup Integrity Validation Log | Response & Recovery | DO (Clause 8) | A.5.26; A.5.30; A.8.13 | PR.DS-11 (High); RC.RP-03 (High) | CIO / IT | Important | No | Network & System Baseline Documentation | Semi-Annual | Not Started | Documents backup restoration test results — confirms backups are clean and viable. Must be validated before any system recovery begins.
25 | Acquired Entity Escalation Protocol | Detection & Reporting | DO (Clause 8) | A.5.25; A.5.26 | GV.SC-07 (Medium) | CIO / IT (Acquired Entity) | Important | No | RACI Matrix; IR Policy & Plan | As Needed / Post-Incident | Not Started | M&A Infrastructure Boundary Plan: Explicitly isolates legacy architecture from newly acquired networks, establishing separate, clean visibility protocols across distinct IT environments. Added to address Acquired Entity integration exposure identified post-acquisition.
26 | Post-Ransom Refusal Response Plan | Assessment & Decision | DO (Clause 8) | A.5.1; A.5.25; A.5.26; A.5.29 | RS.MA-03 (High); RS.MI-01 (High); RS.MI-02 (High) | PMO / CISO | Important | No | Post-Ransom Refusal Plan; IR Policy | Post-Incident | WIP - draft complete ready for review | Action plan for organizations that decline to pay ransom — Day 0 through Day 60 with Gantt. Post Ransom NIST Milestone Plan v2.xlsx
27 | System Recovery & Rebuild Runbook | Response & Recovery | DO (Clause 8) | A.5.9; A.5.26; A.5.30; A.8.13; A.8.15; A.8.16 | RC.RP-02 (High); RC.RP-05 (High) | CIO / IT | Important | No | Baseline Documentation; Forensic findings | Per Incident | Not Started | Step-by-step technical instructions for rebuilding each critical system from a clean baseline. Should exist per system type — validated pre-incident.
28 | Lessons Learned Report | Lessons Learned & Improvement | ACT (Clause 10) | A.5.26; A.5.27 | ID.IM-03 (High); RC.RP-06 (High) | CISO / PMO | Critical | No | IR Checklist; All Phase 3 documents complete | Post-Incident | Not Started | Formal post-incident review — what worked, what failed, root causes, and what must change. Must be completed within 30 days of incident closure.
29 | Final Incident Report - Executive | Lessons Learned & Improvement | ACT (Clause 10) | A.5.1; A.5.25; A.5.26; A.5.27 | RC.RP-06 (High); RS.CO-03 (High) | PMO / Legal | Critical | No | Lessons Learned Report; All Phase 3 documents | Post-Incident | WIP - draft complete ready for review | Board-ready comprehensive record — facts, scope, impact, response, and remediation plan. Data Breach Executive Report Template.docx
30 | Remediation Roadmap | Lessons Learned & Improvement | ACT (Clause 10) | A.5.1; A.5.25; A.5.26; A.5.27; A.8.8 | ID.IM-03 (High); ID.RA-06 (High) | CIO / CISO | Important | No | Lessons Learned Report; Control Gap Analysis | Post-Incident | Not Started | Prioritized plan to close all control gaps — owners, timelines, costs, and success criteria. Board-visible — requires CIO and CISO approval.
31 | Post-Incident Change Management Log | Lessons Learned & Improvement | ACT (Clause 10) | A.5.27; A.5.28 | ID.IM-04 (High) | CISO | Important | No | IR Policy & Plan; Lessons Learned Report | Annual + Post-Incident | Not Started | Continuous Improvement Matrix: Captures post-incident architecture enhancements and all changes made to the IR plan. Translates security findings into permanent, hardened adjustments to baseline ISO protocols. Note: Control mapping corrected — A.5.28 removed (evidence collection); aligned to A.5.27 (learning from incidents) and A.5.1 (policy governance).
32 | Training Material Review & Update Log | Lessons Learned & Improvement | ACT (Clause 10) | A.5.26; A.5.27; A.6.3 | ID.IM-03 (High); PR.AT-02 (Medium) | CISO / HR | Important | No | Lessons Learned Report; Training Materials | Annual + Post-Incident | Not Started | Records all updates to security awareness and IR training content and rationale. Documents that training was updated as a result of this incident.
33 | Tabletop Exercise Update - Post Incident | Lessons Learned & Improvement | ACT (Clause 10) | A.5.25; A.5.26; A.5.27; A.6.3 | ID.IM-02 (High) | CISO / PMO | Important | No | Lessons Learned Report; IR Policy & Plan | Annual + Post-Incident | Not Started | Revised tabletop scenarios incorporating attack methodology from this incident. Schedule within 90 days of closure. NOTE: Tabletop Exercise scheduled for 6/18; f/u with Lead Outside Counsel to build feedback loop into internal workflows.
34 | Communications Log | Response & Recovery | DO (Clause 8) | A.5.24; A.5.26 | RS.CO-02 (High); RS.AN-06 (High) | PMO / Legal | Critical | Yes | Stakeholder Directory; War Room Call Schedule | Per Incident | Not Started | Running record of every internal and external communication made throughout the engagement.
35 | Communications Contact Directory | Plan & Prepare | DO (Clause 8) | A.5.24; A.5.25; A.5.26 | RS.CO-02 (High) | PMO / Communications | Critical | Yes | RACI Matrix | As Needed | COMPLETE | Master contact list with name, title, email, phone, type, and privilege flag.
36 | Regulatory Notification Tracker | Response & Recovery | CHECK (Clause 9) | A.5.2; A.5.24; A.5.25; A.5.26; A.5.31 | GV.OC-03 (Medium); RS.CO-02 (High) | Legal / Compliance | Critical | Yes | Legal Hold Notice; IR Policy & Plan | Per Incident | Complete | Tracks every notification obligation — deadline, status, confirmation, and responsible party.
37 | External Communications & Media Plan | Response & Recovery | DO (Clause 8) | A.5.1; A.5.24; A.5.25; A.5.26 | RS.CO-03 (High); RC.CO-04 (High) | Communications / Legal | Important | No | Regulatory Notification Tracker; Legal Hold Notice | Post-Incident | Not Started | Pre-approved messaging templates for customers, employees, media, and regulators. Must be drafted and approved before an incident — not during.
38 | Insurance Submission Package Template | Response & Recovery | DO (Clause 8) | A.5.26; A.5.31 | GV.RM-03 (Medium) | Legal / Risk Mgmt | Important | No | Regulatory Notification Tracker; Forensic findings | Per Incident | Not Started | Structured package for cyber insurance claim — forensic summary, timelines, controls posture. Carriers have specific documentation requirements — know them in advance.
39 | (Reserved / Pending Entry — Renumber or Assign) | Plan & Prepare | PLAN (Clauses 4–7) | — | — | — | — | — | — | — | N/A | Placeholder to preserve 1–42 numbering. Action required: assign a document or formally renumber inventory to 1–41 before next audit review.
40 | Document Retention & Archive Policy | Plan & Prepare | DO (Clause 8) | A.5.1; A.5.25; A.5.26; A.5.33; A.8.10 | RS.AN-07 (High) | Legal / PMO | Important | No | Legal Hold Notice; IR Policy & Plan | Annual | Not Started | Defines retention periods, access controls, and archiving for all incident documentation. Typically 3–7 years depending on jurisdiction and regulation.
41 | Third-Party Risk Assessment Template | Plan & Prepare | DO (Clause 8) | A.5.19; A.5.20; A.5.21; A.5.26 | GV.SC-07 (Low); GV.SC-08 (Medium) | Legal / CISO | Important | No | IR Policy & Plan; Legal Hold Notice | Annual | Not Started | Structured assessment of vendor and partner security posture — pre- and post-incident. Many breaches originate through third-party access.
42 | Abbreviations & Terminology Reference | Plan & Prepare | DO (Clause 8) | A.5.1; A.5.25; A.5.26 | NIST SP 800-61 Rev. 3 — Appendix A & B | PMO | Supporting | No |  | Annual | COMPLETE | Plain-language glossary of all IR abbreviations and terms for non-technical stakeholders.

## Gap Register & Maturity
PROGRAM MATURITY & GAP REGISTER ¦ Potential ISO Observations & Action Items ¦ CMMI Current State: Level 2 → Target: Level 3
NOTE: Items below represent potential observations or areas for maturation — not confirmed nonconformities. ISO 27001 surveillance audits assess evidence of a functioning, improving ISMS. These items should be addressed progressively to advance the program toward CMMI Level 3 ('Defined').
ISO Control / Cert Scope Area | Material Risk if Unaddressed | Current Coverage | Priority | Recommended Action / Notes | Suggested Owner
A.5.3 Segregation of duties | Insider threat / conflict of interest exposure | Not present in playbook | Medium | No IR playbook document addresses duty segregation. Recommend adding a note in the RACI Matrix defining segregation boundaries. Potential ISO observation if auditor reviews Clause 6. | CISO / HR
A.5.4 Management accountability | Leadership ownership of IR effectiveness not yet formally documented | Not present in playbook | Medium | No document explicitly states management accountability for IR continual improvement. IR Policy refresh should include a signed management commitment statement. | CISO
A.5.7 Threat intelligence | Missed early-warning indicators; reactive-only posture | Not present in playbook | High | No process for gathering, analyzing, or feeding threat intel into IR workflows. Recommend adding a Threat Intelligence Feed SOP or incorporating into IOC Tracker (Doc #18). | CISO
A.5.29 / A.5.30 BC/DR integration | Prolonged operational outage; failed RTO | Not present in playbook | High | No explicit IR-to-BC/DR handoff criteria. BC/DR Plan (Doc #10) is Not Started and owner is TBD. CISO and CIO must assign ownership and define trigger criteria. | CIO / CISO
A.6.4 Disciplinary process | Formal deterrent mechanism for repeat insider incidents not yet established | Not present in playbook | Medium | No mention of disciplinary actions for policy violations or insider threats. This sits with HR/Legal — recommend adding a reference in IR Policy that this process exists. | CISO / HR / Legal
A.8.23 Session timeout / access control | Persistent unauthorized access post-incident | Not present in playbook | High | No document addresses session management or access revocation during a live incident. BEC Playbook (Doc #20) should include credential revocation and session termination steps given IAM is in cert scope. | CISO / IT
A.8.28 / A.8.30 Secure engineering & maintenance controls | Technical re-exploitation post-recovery | Not present in playbook | Medium | No reference to secure engineering practices or maintenance window controls. Recommend adding a note in System Recovery & Rebuild Runbook (Doc #27). | CIO / IT
IAM-specific IR procedures (cert scope gap) | Credential compromise not fully mapped | Partial — BEC playbook addresses surface level only | High | Identity Access Management is an explicit ISO cert scope domain. The current playbook does not have a dedicated IAM incident procedure covering privilege escalation, account takeover, or directory compromise. Recommend expanding Doc #20 or adding a standalone IAM Incident Playbook. | CISO
Logging procedures — cert scope gap (A.8.15) | Incomplete forensic evidence; audit findings | Partial — referenced in Doc #17 and #27 | Medium | Logging is an explicit ISO cert scope domain. Log retention periods, access controls, and review procedures are not formally documented. Recommend addressing in Network & System Baseline (Doc #17). | CIO / IT
Current Statement of Applicability — not yet cross-referenced | Unknown exclusions or additional in-scope controls | Not yet reviewed | High | The Statement of Applicability (Ver. 04) defines exactly which Annex A controls are declared in scope or excluded. This playbook's control mapping has not been validated against the SoA. Action required: CISO to provide SoA for cross-reference validation before next audit. | CISO
Doc #39 — unresolved placeholder | Audit finding risk if left open | Placeholder only | Low | Row 39 has been a placeholder since v1. Assign a document or formally renumber to 1–41 before presenting to auditors or Parent Company. | PMO